## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | SWEN-261-2228-team-project-group-3-bookstore
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a buyer I want to see a list of products so that I choose what to purchase. | Given that I am on the e-store site when I am not on the Products page then I must see a means to navigate to the Products page. | Pass | XH; 7/16/2023; Clicking on the go back button brings you back to the product page. | Pass | JH 8/2/23; go back button still works, nav menu works
| Given that I am not on the Products page when I choose the Products page then I am taken to the Products page. | Pass | XH; 7/16/2023; Clicking on the go back button brings you back to the product page. | Pass | JH 8/2/23; nav menu works
| Given that I am on the Products page when there are no products in the inventory I see a message indicating that that there are no products available. | Pass | XH;7/16/2023; If there is no products the products show up as blank | Pass | JH 8/2/23; we were informed by cross team testing that the "message indicating no products available" wasn't actually being done, so we have fixed that for this sprint.
| Given that I am on the products page when there are products in the inventory then I see each product and short description. | Pass | XH;7/16/2023; If there is a product you may click on the product and it shows the price and the name of the product. | Pass | JH 8/2/23; product info page still works
| Given that I am on the products page when there are products in the inventory then I see a means to add each product to my shopping cart. | Pass | XH; 7/16/2023; You can add the product to a shopping cart | Pass | JH 8/2/23; add to cart button works
Admin Page
As a store admin I want to be able to modify, create, and delete products for sale using the website UI so that I have an easy intuitive way of selling my products in the way that I would like them to be presented. | Given I am an store admin when I view the store website then I expect there to be a button to view the admin page. | Pass | RR; 7/16/2023; worked as expected when user was logged in as admin | Pass | XH; 8/2/2023; Once logged in as admin it takes you to admin page.
| Given I am viewing the admin page when I click a button on the page labelled "Create new product" then I expect to be able to fill in details about a new product I want to sell that will then appear on my storefront. | Pass | RR; 7/16/2023; Worked being able to fill out for new product | Pass | XH; 8/2/2023; Once logged in as admin it takes you to admin page and you may add a product as well.
| Given I am viewing the admin page when I click a button on the page labelled "Edit existing product" then I expect to be able to fill in and change details about an existing product I am selling that appears on my storefront. | Pass | RR; 7/16/2023; Worked being able to edit all fields of product | Pass | XH; 8/2/2023; Once logged in as an admin and you click on an existing product you may edit the details of a product.
| Given I am viewing the admin page when I click a button on the page labelled "Delete existing product" then I expect to be able to select an existing product I am selling that appears on my storefront. | Pass | RR; 7/16/2023; Was able to delete product and see said product removed | Pass | XH; 8/2/2023; Once logged in as an admin if a product exists you may delete the product.
Inventory Page
As a store user I want to be able to view all products for sale using the website UI so that I have an easy intuitive way of buying and viewing products so that I can buy them. | Given I am a user on the store inventory page when I click on a product then I expect to be brought to that product's page | Pass | JH; 7/17/2023; works as expected | Pass | RR; 8/2/23
| Given I am a user when I navigate to the inventory page then I expect to see all products in the store | Pass | JH; 7/17/2023; inventory page shows all products | Pass | RR; 8/2/23
Product Page
As a buyer I want to be able to view products so that I can choose to buy the product. | Given I am an buyer when I open the page then I should be able to view and add the product to my cart. | Pass | JH; 7/17/2023; products page show expected details | Pass | RR; 8/2/23
Shopping Cart Persistence
As a customer, I want persistence across my shopping cart in the store, so that I don’t have to redo adding the products I want to buy into my shopping cart upon logging out and back in, saving me time and effort remembering what was in there. | Given the products in my shopping cart when I visit the website from anywhere then I expect my items to still be in my shopping cart. | Pass | XH; 7/17/2023; The shopping cart does persist and you can add items. So it works as expected. | Pass | RR; 8/2/23
Remove Product From Cart
As a Customer I want to be able to remove items from my cart so that items I no longer want are not in my cart. | Given I submit a request to delete a product from my shopping cart when products exist in my shopping cart then the system should remove the product from my shopping cart and a status code of 200 (OK). | Pass | JH; 7/17/2023; this works with both a curl command and through the UI | Pass | XH; 8/2/2023; This works with both a curl command and through the UI
| Given I submit a request to delete a product from my shopping cart when product does NOT exist in my shopping cart then the system should return a status code of 404 (NOT FOUND). | Pass | JH; 7/17/2023; this also works as expected | Pass | XH; 8/2/2023; The same is true with this except the command is delete.
Add Product to Cart
As a Customer I want to be able to add and remove items from my cart so that I can purchase the items I want. | Given The item is available when I click add to cart then I expect the item to be added to my shopping cart. | Pass | CD; 7/17/2023; works as intended. | Pass | RR; 8/2/23
User Persistence
As am owner I want to login with my username so that the website will authenticate me as the admin and give me administrator powers. | Given I am a user when I login to the website then I expect to have an account and be able to login. | Pass | JH; 7/17/2023; user log in behavior works as expected | Pass | XH; 8/2/23; Once logged into as a customer you may may add and delete things from your cart
User Login Page
As a user of the website I want to be able to login so that I can use the website. | Given I am a customer when I want to login to the website then I expect to be able to login at a login page | Pass | XH; 7/17/2023; When going to the login page you are able to click login and type a name and when a name is typed you login. | Pass | RR; 8/2/23
| Given I am a admin when I want to login to the website then I expect to be able to login at a login page and afterwards be able to access the login page. | Pass | XH; 7/17/2023; When going to the login page you are able to login as a admin. When you login as an admin it will take you to the admin page. | Pass | RR; 8/2/23
User Authetication
As a buyer I want to login with my username so that the website will authenticate me as a buyer. | Given my username as a customer when I login to the website then I expect to be able to login. | Pass | JH; 7/17/2023; works as expected, cart is shown and admin panel is hidden | Pass | RR; 8/2/23
| Given my username as a admin when I login to the website then I expect to login and see my admin privileges. | Pass | JH; 7/17/2023; works as expected, shows the panel only as admin | Pass | RR; 8/2/23
Get Single Product
AS a Developer I WANT to submit a request to get a single product SO THAT I can access the price and quantity. | 1. GIVEN I submit a request for a product in the inventory WHEN the product exists in the inventory THEN the system should return the product I requested and a status code of 200 (OK) | Pass | RR; 7/17/2023; got 200 and was returned product of given ID | Pass | RA; 8/2/2023; got 200 and was returned product of given ID
| 2. GIVEN I submit a request for a product in the inventory WHEN the product does not exist in the inventory THEN the system should report and error and return a status code of 404 (NOT FOUND) | Pass | RR; 7/17/2023; got 404 when requesting product that doesnt exist | Pass | RA; 8/2/2023; got 404 when requesting product ID that doesnt exist
Get Entire Inventory
AS a Developer I WANT to submit a request to get the entire inventory SO THAT I have access to all of the products. | 1. GIVEN I submit a request for the inventory WHEN products exist in the inventory THEN the system should return a list of products and a status code of 200 (OK) | Pass | RR; 7/17/2023; got 200 and returned list of all current products | Pass | RA; 8/2/2023; got 200 and returned list of all current products
| 2. GIVEN I submit a request for the inventory WHEN no products exist in the inventory THEN the system should return an empty list of products and a status code of 200 (OK) | Pass | RR; 7/17/2023; got 200 and returned empty list | Pass | RA; 8/2/2023; got 200 and returned empty list
Create New Product
AS a Developer I WANT to submit a request to create a new product (name, price, quantity) SO THAT it is available to in the inventory. | GIVEN I submit a product object WHEN no product with the given name exists THEN the system should create the product, add it to the inventory, save to the persistent store, and return the product object and a status code of 201 (CREATED) | Pass | RR; 7/17/2023; got 201 and item was created | Pass | RA; 8/2/2023; got 201 and item was created
| GIVEN I submit a product object WHEN a product with the given name already exists THEN the system should return a status code of 409 (CONFLICT) | Pass | RR; 7/17/2023; got 409 and item was not created again | Pass | RA; 8/2/2023; got 409 and item was not created again
Update a Product
AS a Developer I WANT to submit a request to get the entire inventory SO THAT I have access to all products and their details. | 1. GIVEN I submit a request to update the product WHEN that product exists in the inventory THEN the system should return the new product and a status code of 200 (OK) | Pass | RR; 7/17/2023; got 200 and product was succesfully updates | Pass | RA; 8/2/2023; got 200 and product was succesfully updated
| 2. GIVEN I submit a request to update the product WHEN that product does not exist THEN the system should return an error NOT_FOUND (404) | Pass | RR; 7/17/2023; got 404 as product did not exist | Pass | RA; 8/2/2023; got 404 as product did not exist
Delete a Single Product
As a Developer I want to submit a request to delete a single product SO THAT it is no longer in the inventory. | 1. GIVEN I submit a request to delete a product from the inventory WHEN products exist in the inventory THEN the system should remove the product from the inventory and a status code of 200 (OK) | Pass | RR; 7/17/2023; got 200 and product was removed | Pass | XH; 8/2/2023; You will receive the 200 status code and the product will be removed.
| 2. GIVEN I submit a request to delete a product from the inventory WHEN products does NOT exist in the inventory THEN the system should return a status code of 404 (NOT FOUND) | Pass | RR; 7/17/2023; got 404 and no product was removed as product requested for deletion didnt exist | Pass | XH; 8/2/2023; You will receive the 404 status code with the product not being there.
Search for Product
AS a Developer I WANT to submit a request to get the products in the inventory whose name contains the given text SO THAT I have access to only those products. | Given The item exists when I search for the product by name then I expect to be given access to said products. | Pass | RR; 7/17/2023; was given list of all products containing search term | Pass | XH; 8/2/2023; You may search existing products with no issues.
| Given the product does not exist when I try to search for the product then I expect to get nothing back. | Pass | RR; 7/17/2023; when searching for products that dont exist given 404 as since not found | Pass | XH; 8/2/2023; If a product does not exists you cannot search the product.
Shopping Cart Checkout
As a customer, I want to be able to proceed to checkout after adding products to my shopping cart, so that I can actually buy and receive the products I wish to purchase. | GIVEN I am on the shopping cart page, WHEN I click check-out, I EXPECT the items in my cart to be purchased. |  |  | Pass | RA; 8/2/2023
| GIVEN my shopping cart is empty, WHEN I try to check-out, I EXPECT to be told there is nothing in my cart to check out. |  |  | Pass | RA; 8/2/2023
Shopping Cart Page
As a customer I want to be able to checkout my products that I want to buy so that I can have the products for myself. | Given I am a user on the shopping cart page when I click on checkout then I expect to be able to buy the product. |  |  | Pass | RA; 8/2/2023
| Given I am a user when I navigate to the shopping cart page then I expect to see all products I have added to the shopping cart. |  |  | Pass | RA; 8/2/2023
View Purchase History: Enhancement
As a customer I want to see a list of products that I have previously purchased so that I can easily know what I have already purchased from the store. | Given I am a user when I view my purchase history then I expect to see all items I purchased. |  |  | Pass | JH 8/2/23; works as expected
Apply Discount Code: Enhancement
As a Customer I want to be able to apply discount codes so that I have discounted prices. | Given The discount code exist when I apply the discount code at the checkout then the system should discount the item in the checkout. |  |  | Pass | JH 8/2/23; works as expected, no issues here
Delete Discount Code: Enhancement
As an owner I want to be able to erase discount codes or otherwise make them stop working at a given time, so that I can make certain discounts last a limited time and keep use of them rare. | Given I am admin when attempt to delete a discount code then I expect it to be deleted and no longer be able to be used. |  |  | Pass | JH 8/2/23; good work, works as expected
Create Discount Code: Enhancement
As an Owner I want to be able to create discount codes so that Customers may apply them on checkout for discounted prices. | Given I am a store admin when I click on a button in the admin page labelled 'create discount code' then I expect to specify a string that acts as a discount code for a specified amount of discount for users to use in their checkout. |  |  | Pass | JH 8/2/23; works as expected